## Sheet1
Tasks | 2024 | [15 empty] | 2025
| Setembro |  |  | Outubro |  |  |  | Novembro |  |  |  | Dezembro |  |  |  |  | Janeiro |  |  |  | Fevereiro |  |  |  | Março |  |  |  |  | Abril |  |  |  | Maio |  |  |  | Junho |  |  |  |  | Julho |  |  |  | Agosto
| 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
Pausas Letivas /Férias Escolares
Defesa Intermédia / Defesa Final
Plano de Trabalhos - Semestre 1
Revisão da literatura ferramentas open source – 4 semanas
Estudo das diferentes ferramentas SIEM open source disponíveis no mercado – 4 semanas
Análise, escolha e implementação da ferramenta SIEM– 3 semanas
Integração da ferramenta SIEM com outros sistemas; exemplos: firewall, servidores – 4 semanas
Escrita do relatório intermédio – 2 semanas
Plano de Trabalhos - Semestre 2
Modulação de ameaças e ataques a serem testados na ferramenta– 4 semanas
Penetration testing - 5 semanas
Melhoria do SIEM– 4 semanas
Análise dos resultados – 3 semanas
Escrita da dissertação – 3 semanas
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Arranque do Ano Letivo
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Latada
Note on P4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Férias natal
Note on AG4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Páscoa
Note on AL4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Queima das Fitas

## Sheet3
|  | Planeado |  |  |  | Real |  |  |  | Desvio (d)
| Task Number | Data de início | Data de fim | Duração (w) | Acumulado Planeado | Data de início | data de fim | Duração (w) | Acumulado Real | Desvio total | Acumulado
Revisão da literatura ferramentas open source – 4 semanas | T1 |  |  | 4 | 4 |  |  | 5 | 5
Estudo das diferentes ferramentas SIEM open source disponíveis no mercado – 4 semanas | T2 |  |  | 4 | 8 |  |  | 5 | 10
Análise, escolha e implementação da ferramenta SIEM– 3 semanas | T3 |  |  | 3 | 11 |  |  | 3 | 13
Integração da ferramenta SIEM com outros sistemas; exemplos: firewall, servidores – 4 semanas | T4 |  |  | 4 | 15 |  |  | 3 | 16
Escrita do relatório intermédio – 2 semanas | T5 |  |  | 2 | 17 |  |  | 2 | 18
• Modulação de ameaças e ataques a serem testados na ferramenta– 4 semanas | T6 |  |  | 4 | 21 |  |  | 1 | 19
• Penetration testing - 5 semanas | T7 |  |  | 5 | 26 |  |  | 2 | 21
• Melhoria do SIEM– 4 semanas | T8 |  |  | 3 | 29 |  |  | 4 | 25
• Análise dos resultados – 3 semanas | T9 |  |  | 3 | 32 |  |  | 5 | 30
• Escrita da dissertação – 3 semanas | T10 |  |  | 3 | 35 |  |  | 6 | 36

## Sheet1 (2)
Tasks | 2024 | [15 empty] | 2025
| Setembro |  |  | Outubro |  |  |  | Novembro |  |  |  | Dezembro |  |  |  |  | Janeiro |  |  |  | Fevereiro |  |  |  | Março |  |  |  |  | Abril |  |  |  | Maio |  |  |  | Junho |  |  |  |  | Julho |  |  |  | Agosto
| 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
Pausas Letivas /Férias Escolares
Defesa Intermédia / Defesa Final
Plano de Trabalhos - Semestre 1
Revisão da literatura ferramentas open source – 4 semanas
Estudo das diferentes ferramentas SIEM open source disponíveis no mercado – 4 semanas
Análise, escolha e implementação da ferramenta SIEM– 3 semanas
Integração da ferramenta SIEM com outros sistemas; exemplos: firewall, servidores – 4 semanas
Escrita do relatório intermédio – 2 semanas
Plano de Trabalhos - Semestre 2
Modulação de ameaças e ataques a serem testados na ferramenta– 4 semanas
Penetration testing - 5 semanas
Melhoria do SIEM– 4 semanas
Análise dos resultados – 3 semanas
Escrita da dissertação – 3 semanas
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Arranque do Ano Letivo
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Latada
Note on P4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Férias natal
Note on AG4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Páscoa
Note on AL4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Queima das Fitas

## Mid-term Original
Tasks | 2024 | [15 empty] | 2025
| Sep |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Julho |  |  |  | Agosto
| 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
Holidays
Mid and Final Presentation
1º Semester
Siem Background Work – 4 weeks
SIEM Market Research – 4 weeks
SIEM First Analysis and Implementation– 3 Weeks
SIEM Integration – 4 Weeks
Mid-term Report Redaction – 2 weeks
2º Semester
Threat Modeling– 4 weeks
Penetration testing - 5 weeks
SIEM Improvement – 4 weeks
Results Analysis – 3 weeks
Dissertation Redaction – 3 weeks
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Arranque do Ano Letivo
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Latada
Note on P4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Férias natal
Note on AG4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Páscoa
Note on AL4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Queima das Fitas

## Gantt 1S Final
Tasks | 2024 | [15 empty] | 2025
| Sep |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  |  | Jan
| 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4
Holidays
Mid and Final Presentation
1º Semester
Siem Background Work – 4 weeks
SIEM Market Research – 4 weeks
SIEM First Analysis and Implementation– 3 Weeks
SIEM Selection Methodology Draft – 4 Weeks
Mid-term Report Redaction – 2 weeks

## Gantt 2S Final
Tasks
| Jan | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun
| 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
Holidays
Mid and Final Presentation
2º Semester
Case Study Definition– 4 weeks
SIEM Selection Methodology Application- 5 weeks
SIEM Selection Methodology Refinement – 4 Weeks– 4 weeks
Results Analysis – 3 weeks
Dissertation Redaction – 3 weeks
Note on N4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Páscoa
Note on S4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Queima das Fitas